## Check LAN-WAN
Interface | Status | Protocol | Description | Comment |  | Interface | Status | Protocol | Description | Comment
Gi0/1 | down | down | Link to PT-VDCNSWI16 |  |  | Gi0/1 | down | down | Provider-1 | VLAN101
Gi0/2 | up | up | PT-VDCFWM01a int0 TRUNK |  |  | Gi0/2 | up | up | PT-VDCFWM01a int0 TRUNK | VLAN101, 102
Gi0/3 | up | up | PT-VDCFWM01a int2 |  |  | Gi0/3 | up | up | PT-VDCFWM01a int2
Gi0/4 | up | up | PT-VDCFWM01a int3 |  |  | Gi0/4 | up | up | PT-VDCFWM01a int3
Gi0/5 | up | up | VDC-esx1-ilo |  |  | Gi0/5 | up | up | VDC-esx1-ilo
Gi0/6 | down | down |  |  | Vers SDWAN | Gi0/6 | down | down
Gi0/7 | up | up | VDC-esx1-e1 |  |  | Gi0/7 | up | up | VDC-esx1-e1
Gi0/8 | up | up | VDC-esx2-e2 |  |  | Gi0/8 | up | up | VDC-esx2-e2
Gi0/9 | up | up | Link To PT-VDCCDR02 |  |  | Gi0/9 | up | up | Link To PT-VDCCDR02
Gi0/10 | up | up | OBS1 |  |  | Gi0/10 | up | up | OBS1 | Delete after migration
Gi0/11 | down | down |  |  |  | Gi0/11 | down | down
Gi0/12 | down | down |  |  |  | Gi0/12 | down | down
CDR01
PT-LISNSWI01
Interface | Status | Protocol | Description | Comment |  | Interface | Status | Protocol | Description | Comment
Gi0/1 | up | up | Link To PT-VDCNSWI17 |  |  | Gi0/1 | up | up | Link To PT-VDCNSWI17
Gi0/2 | up | up | PT-VDCFWM01b int0 TRUNK |  |  | Gi0/2 | up | up | PT-VDCFWM01b int0 TRUNK | VLAN101, 102
Gi0/3 | up | up | PT-VDCFWM01b int2 |  |  | Gi0/3 | up | up | PT-VDCFWM01b int2
Gi0/4 | up | up | PT-VDCFWM01b int3 |  | Vers SDWAN | Gi0/4 | up | up | PT-VDCFWM01b int3
Gi0/5 | up | up | VDC-esx2-ilo |  |  | Gi0/5 | up | up | VDC-esx2-ilo
Gi0/6 | up | up | VDC-esx2-e1 |  |  | Gi0/6 | up | up | VDC-esx2-e1
Gi0/7 | up | up | VDC-esx1-e2 |  |  | Gi0/7 | up | up | VDC-esx1-e2
Gi0/8 | down | down |  |  |  | Gi0/8 | down | down | Provider-2 | VLAN102
Gi0/9 | up | up | Link To PT-VDCCDR01 |  |  | Gi0/9 | up | up | Link To PT-VDCCDR01
Gi0/10 | up | up | OBS2 |  |  | Gi0/10 | up | up | OBS2 | Delete after migration
Gi0/11 | down | down |  |  |  | Gi0/11 | down | down
Gi0/12 | down | down |  |  |  | Gi0/12 | down | down
Public IP
Circuit | Public IP Scope | Gateway | Public IP FW-a | Public IP FW-b
Circuit 1
Circuit 2

## Prerequisite - Central FW
To be filled by Local IT Manager
To be filled by Central Network Team
Migration Checklist : UK-SEV
Pré-requis
Migration Type | FW Interfaces |  |  | 2 Cisco Routers managed by OBS with Ipanema device
CDR Interfaces
Site type
| SFP availables ? |  |  | Unnecessary ? Vérification terminaison RJ45/SFP Router Provider
Zscaler IP Public declaration
Console cable
Configuration deployment
Type | Element | Amount | Done | Comments
Devices and cables | Core switch | 2
| Firewalls | 2
| Console cable for the Firewall | 1
| Power cable for the Firewalls | 2 |  | Sent with the firewalls
| RJ45 cables for office core switch-FW | 6
| RJ45 cables for HA firewalls | 1
Free ports | On FW | 6 |  | 3 ports each FW
| On Access switch | 6 |  | 3 ports on each switch (if it's a cluster)
Installation | Firewalls installed on same rack as CDR | -
| Rack unit for each Firewall | 2
| Power supply on UPS for each firewall | -
2
1
No
Yes
No
Yes
No
Plant
Office
Yes
No
Yes
No

## PLAN d'action
Planification | Actions
Role | # | Equipement | Action | Delay (mn) | Commentaire
BEL | 1 | Pre-requisite | * Contact IT local (check console cable drivers, Mobile connexion, local admin on PC) * Check cabling ( rack pictures, number of cables ) * Level 1 architecture before and after migration * Recuperer les references des routeurs OBS * Declare the public ip on Zscaler plateform
BEL | 2 | Configuration switch Vale de Cambra | * Creation and propagation of Vlan 101 & Vlan 102 on Switch PT-VDCCDR. * Configuration of new interfaces Gi0/1 on PT-VDCCDR01 for ISP1 (in access Vlan 101). * Configuration of new interfaces Gi0/1 on PT-VDCCDR01 with VLAN101 & 102 * Configuration of new interfaces Gi0/8 on PT-VDCCDR02 for ISP2 (in access Vlan 102). * Configuration of new interfaces Gi0/8 on PT-VDCCDR02 with VLAN101 & 102 * Add VLAN 101 & 102 to the interface Gi0/2 of PT-VDCCDR01 & 02. |  | *IP public configuré sur le Master Engine. La VIP doit être configurée sur le FW Usine
BEL | 3 | Configuration PT-VDCFWM01 | * Add vlan interface 101 on interface 0 : CVI : 62.48.225.241 NDIa : 62.48.225.242 NDIb : 62.48.225.243 Add vlan interface 102 on interface 0 : CVI : 195.23.78.42 NDIa : 195.23.78.43 NDIb : 195.23.78.44 *Add Public IP on Control Interface as backup (Interfaces > Interface Options) and Private IP stay the primary. * Creation of traffic handler : Outbound-PT-VDC-Internet ; constituted of : nlink-PT-VDC-WAN 1 (@Public IP) & nlink-PT-VDC-WAN 2 (@Public IP) * Creation of policy NAT : 'Office, Office_Wifi, Mobile_Wifi and infra ) to Internet' * Activate NAT policy * Replace the default route by 172.16.0.0/12 on the routing table *Add default route on the new interface with the nlink as gateway * Copy the policy internet - Bel standard direct access policy |  | Pour Creation interface sur le firewall: ajouter mac address 00:00:5e:00:00:1X (X étant le numero de l'interface) Ajout adresse IP sur l'interface X Au niveau du interface interco, suppression route par défaut et ajout route 172.16.0.0/12 1. Création des nlink pour les 2 opérateurs (SDWAN > Trafic Handler > Static Netlink) 2. Création du trafic Handler (SDWAN > Trafic Handler > New (Outbond multi-link) Copier les règes 5.6.24.3 sur fw MAD (Internet -> Grp-Net-Bel-Internet) Copier les règles 5.6.24.4 sur FW MAD (outbound-FR -> Pare-feu du site) Second push : mettre IP VLAN400/200 en BACKUP pour control interface
BEL | 4 | Configuration PT-VDCFWM01 | * Creation of traffic handler : Outbound-PT-VDC-Internet ; constituted of : nlink-PT-VDC-WAN 1 (@Public IP) & nlink-PT-VDC-WAN 2 (@Public IP) * Creation of policy NAT : 'Office, Office_Wifi, Mobile_Wifi and infra ) to Internet' * Activate NAT policy |  | 1. Création des nlink pour les 2 opérateurs (SDWAN > Trafic Handler > Static Netlink) 2. Création du trafic Handler (SDWAN > Trafic Handler > New (Outbond multi-link)
Push
BEL | 5 | Configuration FR-CLAFWI01 | * Create New Network Group (Grp-Net-Bel-PT-VDC) for the site with all netwok subnet * Add Group Network PT-VDC (Grp-Net-Bel-PT-VDC) on the Bel-site-to-site VPN policy (Forcepoint<->Forcepoint)
BEL | 6 | Configuration PT-VDCFWM01 | * Creation of Zscaler Gateways : ~ 'PT-Zscaler' with 2 nodes (Mad3-vpn.zscalertwo.net : 165.225.92.26 & par2-vpn.zscalertwo.net: 165.225.76.35) * Activate endpoint on the Gateway PT-VDCFWM01 (after creation of interface 6 & 7) * Creation of VPN policy based VPN : BEL-PT-VDC-WAN 1-Zscaler & BEL-PT-VDC-WAN 2-Zscaler * Activate tunnels in policy based vpn * Modification of policy IPV4 : Belnet to Internet through VPN Zscaler (Enforced ) * Activate IPV4 policy |  | Pour créer IT-Zscaler, aller dans SDWAN > Policy-Based VPN > Bel-PT-LIS-zscaler. Il faut ensuiter "Edit" et créer un New External VPN Gateway "PT-Zscaler" et ajouter les différents nœuds Zscaler. Test connectivité sans Tunnel Zscaler. Si tests concluant, ajout du Enforce VPN Zscaler dans la règle.
BEL | 7 | Configuration Zscaler | * Add the vpn credentials then Location Mgmt * Modify the tunnel pre-shared key (Administration > VPN Credentials) |  | Ne pas oublier la sub-location Mobile en desactivant l'authentification users
BEL | 8 | Configuration PT-VDCFWM01 | * Add security Policies section for DHCP purpose then add DHCP traffic policies to be allowed through the VPN Full mesh * Add security policy to allow traffic for local subnets (from Grp-Net-Bel-PT-VDC to Grp-Net-Bel-PT-VDC) * Enforce Wifi and Mobile traffic flows on Zscaler VPN Tunnel Link1 * Enforce Office and Server traffic (HTTPS, HTTP and FTP Services) to be allow through Zscaler VPN Tunnel Link2 * Enforce All other traffic (site to site or Site to Dc) on Full_Mesh_Corporate_VPN
BEL | 9 | Configuration FR-CLAFWI01 | * Add the Engines on claranet firewall to allow the engines with public ip then PUSH on claraniet firewall |  | * Update Group Network PT-VDC (Grp-Net-Bel-PT-VDC) on the Bel-site-to-site VPN policy (Forcepoint<->Forcepoint) on FR-CLAFWI01
BEL | 10 | Configuration SE-HELFWU01 | * Change the DNS from private dns to the public dns (KEMP) * Change the location (outside_bel) * Add the engine to the remote firewall groupe * Change the ip of the engine with sg-reconfigure * Configure the smc public ip address (85.208.192.10) on both firewall (sg-reconfigure) |  | Mettre l'IP publique de la SMC : 85.208.192.10 (à faire sur les deux FW) Etape Sg-reconfigure Connecter en 4G pour éviter la perte de connectivité générer la clé OTP : clic droit 'save initial configuration' > View Details Après avoir effectuer le sg-reconfigure sur les deux-pare-feux, il faut push de nouveau la configuration Configuration -> Install Policy Après la fin du sg-reconfigure, ajouter les groupes BE-BRL sur le pare-feu de CLA01
BEL | 11 | Configuration MAN 1 & 2 | * Deactivate option "Allow Conncetions from local DHCP Relay to Remote DHCP server" * Add the Firewall object (PT-VDCFWM01) on the Bel_Full_Mesh_Corporate_VPN * Enforce All other traffic (site to site or Site to Dc) on Full_Mesh_Corporate_VPN * ip route 172.16.182.0 255.255.255.0 172.19.111.17 name PT-VALE DE CAMBRA * ip route 172.17.182.0 255.255.255.0 172.19.111.17 name PT-VALE DE CAMBRA * ip route 172.17.183.0 255.255.255.0 172.19.111.17 name PT-VALE DE CAMBRA * ip route 172.18.182.0 255.255.254.0 172.19.111.17 name PT-VALE DE CAMBRA * ip route 172.20.182.0 255.255.254.0 172.19.111.17 name PT-VALE DE CAMBRA * ip route 172.22.182.0 255.255.255.0 172.19.111.17 name PT-VALE DE CAMBRA * ip route 172.28.182.0 255.255.254.0 172.19.111.17 name PT-VALE DE CAMBRA * ip route 10.4.32.0 255.255.224.0 172.19.111.17 name PT-VALE DE CAMBRA |  | * Policies > Automatic Rules * Update Group Network PT-LIS (Grp-Net-Bel-PT-VDC) on the Bel-site-to-site VPN policy (Forcepoint<->Forcepoint) on FR-CLAFWI01 ip route 172.17.182.0 255.255.254.0 172.19.111.17 name PT-VALE DE CAMBRA 172.19.111.17 : CLARANET2
PUSH SUR TOUS LES FIREWALLS DU FULL MESH
BEL | 12 | Monitoring | * Update Monitoring Tools * Update Groupe Dataxion * Send an Email to OBS to stop supervion on old obs router * Send an Email to Dataxion for the new firewall supervision * Collect ISP information (name of provider, line bandwith, incident mgmt, contacts etc....)

## cahier de test pré-Opé
| Cahier de tests applicatifs et fonctionnels | Ver 1.0 | Change | Status
FEUILLE DE ROUTE
| Quoi | Quand | Qui | NoK/Ok
1 | Faire un état des lieux de la MAP de supervision WhatsUp Gold (172.18.37.119) |  | François/Julien
2 | Accessibilité des réseaux Intrinsec (ping 172.19.17.45) |  | François/Julien
3 | Accès Internet |  | ITM/ITC
4 | Connectivité Outlook et Lync |  | ITM/ITC
5 | Vérifier l'état du bluecoat et vérifier que les flux sont bien optimisés. |  | François/Julien

## cahier de test post-Opé
| Cahier de tests applicatifs et fonctionnels | Ver 1.0 | Change | Status
FEUILLE DE ROUTE
| Quoi | Quand | Qui | NoK/Ok
1 | Faire un état des lieux de la MAP de supervision WhatsUp Gold (172.18.37.119) |  | François/Julien
2 | Accessibilité des réseaux Intrinsec (ping 172.19.17.45) |  | François/Julien
3 | Accès Internet |  | ITM/ITC
4 | Connectivité Outlook et Lync |  | ITM/ITC
5 | Vérifier l'état du bluecoat et vérifier que les flux sont bien optimisés. |  | François/Julien