## Check LAN-WAN
Interface | Status | Protocol | Description | Comment |  | Interface | Status | Protocol | Description | Comment
Vl1 | admin down | down |  |  |  | Vl1 | admin down | down
Vl200 | [5 empty] | Vl200
Gi0/1 | Gi0/1 | up | up | Link to SW-HELNSWI02 |  | Gi0/1
Gi0/2 | Gi0/2 | up | up | Link to SE-HELNSWI01 |  | Gi0/2
Gi0/3 | Gi0/3 | up | up |  |  | Gi0/3
Gi0/4 | Gi0/4 | up | up | SE-HELFWU01a port 0 | Vers SDWAN | Gi0/4
Gi0/5 | Gi0/5 | up | up | SE-HELFWU01a port 4 |  | Gi0/5
Gi0/6 | Gi0/6 | up | up | SE-HELFWU01a port 5 |  | Gi0/6
Gi0/7 | Gi0/7 | up | up | Link to OBS1 |  | Gi0/7
Gi0/8 | Gi0/8 | up | up | Link to SE-HELNCDR02 |  | Gi0/8
Gi0/9 | Gi0/9 | down | down |  |  | Gi0/9
Gi0/10 | Gi0/10 | down | down |  |  | Gi0/10
CDR01
CDR02
Interface | Status | Protocol | Description | Comment |  | Interface | Status | Protocol | Description | Comment
Vl1 | admin down | down |  |  |  | Vl1 | admin down | down
Vl200 | up | up |  |  |  | Vl200 | up | up
Gi0/1 | down | down | Link To UK-SEVNSW00 | Decommissionned |  | Gi0/1 | down | down | Provider-2 | VLAN102
Gi0/2 | down | down | Link To UK-SEVNSW02 | Decommissionned |  | Gi0/2 | down | down | UK-SEVFW01b int X | VLAN101
Gi0/3 | down | down | Link To UK-SEVNSW01 | Decommissionned |  | Gi0/3 | down | down | UK-SEVFW01b int X | VLAN102
Gi0/4 | up | up | Link To UK-SEVNSW04 |  | Vers SDWAN | Gi0/4 | up | up | Link To UK-SEVNSW04
Gi0/5 | down | down | Interco |  |  | Gi0/5 | down | down | Interco
Gi0/6 | down | down | OBS2 |  |  | Gi0/6 | down | down | OBS2
Gi0/7 | up | up | OBS2 |  |  | Gi0/7 | up | up | OBS2 | DOWN
Gi0/8 | up | up | Link To UK-SEVCDR01 |  |  | Gi0/8 | up | up | Link To UK-SEVCDR01
Gi0/9 | up | up | UK-SEVFW01b int 0 |  |  | Gi0/9 | up | up | UK-SEVFW01b int 0
Gi0/10 | up | up | UK-SEVFW01b int 2 |  |  | Gi0/10 | up | up | UK-SEVFW01b int 2
Public IP
Circuit | Public IP Scope | Gateway | Public IP FW-a | Public IP FW-b
Circuit 1
Circuit 2

## Prerequisite - Central FW
To be filled by Local IT Manager
To be filled by Central Network Team
Migration Checklist : UK-SEV
Pré-requis
Migration Type | FW Interfaces |  |  | 2 Cisco Routers managed by OBS with Ipanema device
CDR Interfaces
Site type
| SFP availables ? |  |  | Unnecessary ? Vérification terminaison RJ45/SFP Router Provider
Zscaler IP Public declaration
Console cable
Configuration deployment
Type | Element | Amount | Done | Comments
Devices and cables | Core switch | 2
| Firewalls | 2
| Console cable for the Firewall | 1
| Power cable for the Firewalls | 2 |  | Sent with the firewalls
| RJ45 cables for office core switch-FW | 6
| RJ45 cables for HA firewalls | 1
Free ports | On FW | 6 |  | 3 ports each FW
| On Access switch | 6 |  | 3 ports on each switch (if it's a cluster)
Installation | Firewalls installed on same rack as CDR | -
| Rack unit for each Firewall | 2
| Power supply on UPS for each firewall | -
2
1
No
Yes
No
Yes
No
Plant
Office
Yes
No
Yes
No

## PLAN d'action
Planification | Actions
Role | # | Equipement | Action | Delay (mn) | Commentaire
| 0 | Prerequis | * Contact IT local (check console cable drivers, Mobile connexion, local admin on PC) * Check cabling ( rack pictures, number of cables ) * Level 1 architecture before and after migration * Retrieve OBS routers reference on OBS portal * Declare the public ip on Zscaler plateform
BEL | 1 | Configuration switch Matosinohs | * Creation and propagation of Vlan 101 on Switch SE_HELCDR1 & SE-HELCDR2 * Configure interface gig1/0/9 for WAN _OBS1 as access vlan 101 on SE-HELCDR1 * Configure interface gig1/0/9 for WAN _OBS2 as access vlan 102 on seèHELCDR2 * Configuration of new interfaces Gi0/10 on SE_HELCDR1 for ISP1 (in access Vlan 101). * Configuration of new interfaces Gi0/10 on SE_HELCDR2 for ISP2 (in access Vlan 102). *add vlan 101 on interfaces gig0/4 & gi0/5 on both CDR (for the firewall as we do not have enough interfaces on CDRs)
BEL | 2 | Cablâge Switch sur Routeurs Operateur | * On port Gi0/9 of switch SE-HELCDR02 connect the fwb Interface * On port Gi1/0/10 of switch SE-HELCDR01 connect the ISP2 Interface ------------------------------------------------------------------ * On port Gi0/9 of switch SE-HELCDR01 connect the fwa interface * On port Gi0/10 of swtich SE-HELCDR01 Connect the ISP1 Interface |  | After circuit testing, delete OBS/Switch Interco (gi0/7)
BEL | 3 | Configuration SE-HELFWU01b | * Add Virtual interfaces on interface 2 : CVI : 195.67.13.19/28 fwa: 195.67.13.20/28 fwb: 195.67.13.21/28 *Add Public IP on Control Interface as backup (Interfaces > Interface Options) and Private IP stay the primary. * Creation of traffic handler : Outbound-SE-HEL-Internet ; constituted of : nlink-SE-HEL-WAN 1 (@Public IP) * Creation of policy NAT : 'Office, Office_Wifi, Mobile_Wifi and infra ) to Internet' * Activate NAT policy * Replace the default route by 172.16.0.0/12 on the routing table *Add default route on the new interface with the nlink as gateway * Copy the policy internet - Bel standard direct access policy |  | Pour Creation interface sur le firewall: ajouter mac address 00:00:5e:00:00:1X (X étant le numero de l'interface) Ajout adresse IP sur l'interface X Au niveau du interface interco, suppression route par défaut et ajout route 172.16.0.0/12 1. Création des nlink pour les 2 opérateurs (SDWAN > Trafic Handler > Static Netlink) 2. Création du trafic Handler (SDWAN > Trafic Handler > New (Outbond multi-link) Copier les règes 5.6.24.3 sur fw MAD (Internet -> Grp-Net-Bel-Internet) Copier les règles 5.6.24.4 sur FW MAD (outbound-FR -> Pare-feu du site)
PUSH
BEL | 4 | Configuration FR-CLAFWI01 | * Check the Network Group (Grp-Net-Bel-SE-HEL) for the site with all netwok subnet * Add Group Network SE-HEL (Grp-Net-Bel-SE-HEL) on the Bel-site-to-site VPN policy (Forcepoint<->Forcepoint)
BEL | 7 | Configuration SE-HELFWU01 | * Creation of Zscaler Gateways : * Activate endpoint on the Gateway SE-HELFWU01 (after creation of interface 3) * Creation of VPN policy based VPN : BEL-SE-HEL-WAN 1-Zscaler & BEL-SE-HEL-WAN 2-Zscaler * Activate tunnels in policy based vpn * Modification of policy IPV4 : Belnet to Internet through VPN Zscaler (Enforced ) * Activate IPV4 policy |  | Pour créer IT-Zscaler, aller dans SDWAN > Policy-Based VPN > Bel-SE-HEL-zscaler. Il faut ensuiter "Edit" et créer un New External VPN Gateway "UK-Zscaler" et ajouter les différents nœuds Zscaler. Test connectivité sans Tunnel Zscaler. Si tests concluant, ajout du Enforce VPN Zscaler dans la règle. Ajoute dans l'onglet "Sites" tous les réseaux lors de l'ajout VPN Gateway Puis dans VPN>Endpoint, désactiver les tunnels avec ip privée
| 6 | Configuration Zscaler | * Add the vpn credentials then Location Mgmt * Modify the tunnel pre-shared key (Administration > VPN Credentials) |  | Ne pas oublier la sub-location Mobile en desactivant l'authentification users
BEL | 8 | Configuration SE-HELFWU01 | * Add security Policies section for DHCP purpose then add DHCP traffic policies to be allowed through the VPN Full mesh * Add security policy to allow traffic for local subnets (from Grp-Net-Bel-SE-HEL to Grp-Net-Bel-SE-HEL) * Enforce Wifi and Mobile traffic flows on Zscaler VPN Tunnel Link1 * Enforce Office and Server traffic (HTTPS, HTTP and FTP Services) to be allow through Zscaler VPN Tunnel Link1 * Enforce All other traffic (site to site or Site to Dc) on Full_Mesh_Corporate_VPN
|  | Configuration FR-CLAFWI01 | * Add the Engines on claranet firewall to allow the engines with public ip then PUSH on claraniet firewall |  | * Update Group Network SE-HEL (Grp-Net-Bel-SE-HEL) on the Bel-site-to-site VPN policy (Forcepoint<->Forcepoint) on FR-CLAFWI01
BEL | 11 | Configuration SE-HELFWU01 | * Change the DNS from private dns to the public dns (KEMP) * Change the location (outside_bel) * Add the engine to the remote firewall groupe * Change the ip of the engine with sg-reconfigure * Configure the smc public ip address (85.208.192.10) on both firewall (sg-reconfigure) |  | Mettre l'IP publique de la SMC : 85.208.192.10 (à faire sur les deux FW) Etape Sg-reconfigure Connecter en 4G pour éviter la perte de connectivité générer la clé OTP : clic droit 'save initial configuration' > View Details Après avoir effectuer le sg-reconfigure sur les deux-pare-feux, il faut push de nouveau la configuration Configuration -> Install Policy Après la fin du sg-reconfigure, ajouter les groupes BE-BRL sur le pare-feu de CLA01
BEL | 10 | Configuration MAN 1 & 2 | * ip route 172.16.70.0 255.255.255.0 172.19.111.17 name SE-HELSINGBORG * ip route 172.17.70.0 255.255.255.0 172.19.111.17 name SE-HELSINGBORG * ip route 172.17.71.0 255.255.255.0 172.19.111.17 name SE-HELSINGBORG * ip route 172.18.70.0 255.255.254.0 172.19.111.17 name SE-HELSINGBORG * ip route 172.20.70.0 255.255.254.0 172.19.111.17 name SE-HELSINGBORG * ip route 172.28.70.0 255.255.255.128 172.19.111.17 name SE-HELSINGBORG * ip route 172.28.71.0 255.255.255.128 172.19.111.17 name SE-HELSINGBORG * ip route 172.28.71.128 255.255.255.192 172.19.111.17 name SE-HELSINGBORG * ip route 172.16.71.240 255.255.255.240 172.19.111.17 name SE-HELSINGBORG |  | ip route 172.17.78.0 255.255.254.0 172.19.111.22 name SE-HELSINGBORG (summary)² 172.19.111.17 : CLARANET2
| 9 | Configuration SE-HELFWU01 | * Add the Firewall object (SE-HELFWU01) on the Bel_Full_Mesh_Corporate_VPN
PUSH SUR TOUS LES FIREWALLS DU FULL MESH
BEL | 12 | Monitoring | * Update Monitoring Tools * Update Groupe Dataxion * Send an Email to OBS to stop supervion on old obs router * Send an Email to Dataxion for the new firewall supervision * Collect ISP information (name of provider, line bandwith, incident mgmt, contacts etc....)

## cahier de test pré-Opé
| Cahier de tests applicatifs et fonctionnels | Ver 1.0 | Change | Status
FEUILLE DE ROUTE
| Quoi | Quand | Qui | NoK/Ok
1 | Faire un état des lieux de la MAP de supervision WhatsUp Gold (172.18.37.119) |  | François/Julien
2 | Accessibilité des réseaux Intrinsec (ping 172.19.17.45) |  | François/Julien
3 | Accès Internet |  | ITM/ITC
4 | Connectivité Outlook et Lync |  | ITM/ITC
5 | Vérifier l'état du bluecoat et vérifier que les flux sont bien optimisés. |  | François/Julien

## cahier de test post-Opé
| Cahier de tests applicatifs et fonctionnels | Ver 1.0 | Change | Status
FEUILLE DE ROUTE
| Quoi | Quand | Qui | NoK/Ok
1 | Faire un état des lieux de la MAP de supervision WhatsUp Gold (172.18.37.119) |  | François/Julien
2 | Accessibilité des réseaux Intrinsec (ping 172.19.17.45) |  | François/Julien
3 | Accès Internet |  | ITM/ITC
4 | Connectivité Outlook et Lync |  | ITM/ITC
5 | Vérifier l'état du bluecoat et vérifier que les flux sont bien optimisés. |  | François/Julien